## Tiered Training
Faculty Digital Readiness – Tiered Training Framework
Tier | Target Audience | Focus Areas | Mode & Duration | Expected Outcome
Tier 1 – Awareness | All faculty | NAAC revised framework, OBE basics, DigiLocker/ABC, NAD, SWAYAM, NPTEL overview | Online MOOC + webinar, 1 week | 100% faculty NAAC-literate
Tier 2 – Practitioner | Subject teachers | LMS (Moodle/Google Classroom), H5P, OER creation, e-assessment, plagiarism tools, rubric design | Blended FDP, 4 weeks | Every teacher runs a digital classroom
Tier 3 – Advanced | Dept. coordinators | CO–PO mapping software, attainment analytics, AI tools for pedagogy, learning analytics | Hands-on workshop, 2 weeks | Data-driven OBE delivery
Tier 4 – Master Trainers / IQAC | IQAC members, HoDs | Virtual audit prep, AQAR auto-generation, SSR evidence repositories, data validation | Certification programme, 3 weeks | Institution audit-ready

## Engagement Mechanisms
Engagement Mechanisms to Sustain Digital Readiness
Activity | Frequency | Purpose | Key Deliverable
Teaching Competitions | Annual | Reward best digital classroom & OBE innovators | Recorded lessons + learner analytics
Seminars | Monthly | Share digital pedagogy practices | Concept notes, recordings
Conferences | Annual (National) | Showcase research on virtual accreditation | UGC-CARE proceedings
Workshops | Monthly | Hands-on skills (Canva, H5P, Moodle, Power BI, AI tools) | Faculty-built artefacts
Hackathons / Bootcamps | Biannual | Build SSR-ready evidence portfolios in 48 hrs | Criterion-wise evidence packs
Peer Learning Circles | Fortnightly | Departmental communities of practice | Best-practice repository
Webinars by NAAC/NPTEL/INFLIBNET | Quarterly | Expert exposure | Certificates + recordings

## 12-Month Roadmap
12-Month Plan of Action
Month | Phase | Key Activities | Milestone / KPI
1–2 | Diagnose | Needs assessment, infrastructure audit, master-trainer selection | Baseline readiness score
3–4 | Awareness | Tier 1 MOOC rolled out institution-wide | ≥90% faculty enrolled
5–6 | Practitioner Training | Tier 2 FDPs; launch central evidence repository | All depts on LMS
7–8 | Showcase | Teaching competitions + first national workshop | Awards + 50+ OER units
9–10 | Advanced Skilling | Tier 3 training; CO–PO attainment dashboards go live | Dashboards in 100% programmes
11 | Mock Audit | IQAC conducts mock virtual NAAC audit | Readiness ≥85%
12 | Accreditation & Review | National conference + AQAR submission + impact review | AQAR submitted; gap report

## Monitoring KPIs
Monitoring & Outcome Metrics
KPI | Unit | Target (Year 1) | Owner
Faculty certified – Tier 1 | % | 100% | IQAC
Faculty certified – Tier 2 | % | 75% | IQAC + HoDs
Faculty certified – Tier 3 | % | 30% | Dept. Coordinators
OER / e-content units uploaded per teacher | Count | ≥4 | Faculty
LMS active usage | % courses | 100% | HoDs
CO–PO attainment dashboards live | % programmes | 100% | IQAC
Virtual audit readiness score | % | ≥85% | IQAC
Student satisfaction (digital learning) | Score /5 | ≥4.0 | Principal